## Instructions
Please follow these instructions to ensure that the project you are trying to upload goes through without any problems
Project Details |  | Project Assessment
*Required |  | *First row is always required
Sample Data |  | Sample Data
*Project Title | New Product Launch | *Date | *Completeness % | *Timeliness %
*Project Description | Marketing Campaign for 4Q | 2018-11-05 | 0 | 100
*Start Date | 2018-11-05 | 2018-11-06 | 5 | 90
*End Date | 2018-12-05 | 2018-11-07 | 12.75 | 82.75
Actual End Date |  | 2018-11-08 | 15.5 | 80
*Status | Planning | 2018-11-09 | 19.01 | 77.93
Important Notes
Start Date End Date Actual End Date | This must be a valid date | Date | Should start from the Project Start Date
Date must be sequential
| End date must always be greater than your start date | Completeness Timeliness | Should have 2 decimal places
If new project: Completeness = 0.00 Timeliness = 100.00
Format: YYYY-MM-DD
Actual End Date is required if the status of the project is Complete
Status | Must be a valid input from the list below: - Planning - Ongoing - Complete - Archived
Tasks
*Required for All, *Required for Tasks
Sample Data
*Task Title | Buy Menu Boards
*Start Date | 2018-11-05
*End Date | 2018-11-10
Actual End Date
*Status | Ongoing
Remarks
*Category | 3
*Task Parent | Prepare Advertisments
*R (Responsible) | Winnie The Pooh
*A (Accountable) | Mickey Mouse, Donald Duck
*C (Consulted) | Donald Duck
*I (Informed) | Mickey Mouse
Important Notes
Start Date End Date Actual End Date | This must be a valid date
End date must always be greater than your start date
Dates must be in the range you have set in the Project Details
Format: YYYY-MM-DD
Actual End Date is required if the status of the task is Complete
Status | Must be a valid input from the list below: - Planning - Ongoing - Complete
Remarks | This field is required if task is delayed
Category | Must be a valid input from the list below: - 1 (Main Activity) - 2 (Sub Activity) - 3 (Task)
Task Parent | This must have a valid Task Title from the list of tasks in the same sheet
Task Parent must either be a Category 1 (Main Activity) or Category 2 (Sub Activity)
R (Responsible) A (Accountable) C (Consulted) I (Informed) | This is required for Category 3 (Tasks)
This must be a name of a valid employee
Format: FIRSTNAME LASTNAME
R - One employee only A - As many as it needs C - As many as it needs I - As many as it needs
Use a comma (, ) to separate multiple ACI

## Project Details
Project Title
Project Description
Start Date
End Date
Actual End Date
Project Status

## Project Assessment
Date | Completeness | Timeliness
0

## Tasks
Task Title | Start Date | End Date | Actual End Date | Status | Remarks | Category | Task Parent | R | A | C | I

## Main Activity Progress
Date | Completeness | Timeliness | Main Activity